Campaign brief and plan

[Campaign name]  ·  [Dates]  ·  Owner: [Name]

Guidance: Sign the brief off before any asset is produced. Most campaign waste happens because production started before the proposition was agreed.

Campaign brief

Campaign name

Guidance: Short and specific enough to search for later.

[ ................................................................................ ]

Why now

Guidance: The trigger. A launch, a season, a competitor move, a deadline.

[ ................................................................................ ]

Objective

Guidance: One measurable outcome with a target and a date.

[ ................................................................................ ]

Audience

Guidance: Who, and what they currently believe or do.

[ ................................................................................ ]

Single-minded proposition

Guidance: The one thing to communicate. If it needs a comma, it is two things.

[ ................................................................................ ]

Offer or call to action

Guidance: Exactly what you want them to do.

[ ................................................................................ ]

Channels

Guidance: Where it runs and what each channel contributes.

[ ................................................................................ ]

Assets required

Guidance: Every asset, with an owner and a due date.

[ ................................................................................ ]

Budget

Guidance: Media, production and tools, separately.

[ ................................................................................ ]

Success measures

Guidance: Primary metric plus the guardrail metric that must not get worse.

[ ................................................................................ ]

Risks and dependencies

Guidance: What could stop this, and who needs to unblock it.

[ ................................................................................ ]

Timeline

Guidance: Adjust the typical durations to your own campaign. Keep the phases.

| Phase | Typical timing | What happens | Owner | Done? |
| --- | --- | --- | --- | --- |
| Plan | Weeks 1 to 2 | Brief signed off, audience and offer agreed, measurement plan written. |  |  |
| Produce | Weeks 2 to 4 | Assets built and approved, landing pages live, tracking tested end to end. |  |  |
| Launch | Week 5 | Staged launch, delivery checked within 24 hours, obvious errors fixed fast. |  |  |
| Optimise | Weeks 5 to 8 | Weekly review of the primary metric. Reallocate budget. Kill what is not working. |  |  |
| Review | Week 9 | Written post-campaign review while people still remember the detail. |  |  |

Budget

Guidance: Split media from production. Blending them hides which part is actually expensive.

| Line | Planned | Actual | Notes |
| --- | --- | --- | --- |
| Media spend |  |  |  |
| Production |  |  |  |
| Tools / licences |  |  |  |
| Contingency |  |  |  |
| Total |  |  |  |

Post-campaign review

Guidance: Complete this within two weeks of the campaign ending, while people still remember the detail.

Did we hit the primary metric? By how much, and against what target?

[ ................................................................................ ]

Which channel produced the outcome most efficiently?

[ ................................................................................ ]

What did we assume that turned out to be wrong?

[ ................................................................................ ]

Which asset performed best, and can we reuse it?

[ ................................................................................ ]

What would we cut entirely if we ran this again?

[ ................................................................................ ]

What should become permanent rather than campaign-only?

[ ................................................................................ ]

Campaign shapes that tend to work

Example figures are illustrative and are used to show how the template works. They are not real client data and are not benchmarks.

Seasonal retail push (illustrative)

Proposition: One deadline-driven offer repeated across every channel.

Structure: Two weeks of teaser content, one week of offer, a 48-hour closing reminder.

What to plan for: The closing reminder usually produces a disproportionate share of conversions. Plan for it rather than adding it late.

B2B webinar to pipeline (illustrative)

Proposition: A specific problem solved live by someone credible.

Structure: Four weeks of registration driving, the event, then a three-email follow-up split by attended or not.

What to plan for: The follow-up sequence generates more pipeline than the event. Budget time for it before the event, not after.

Product launch (illustrative)

Proposition: One capability, one audience, one before-and-after.

Structure: Existing customers first, then waitlist, then public. Staged over three weeks.

What to plan for: Launching to existing customers first surfaces the messaging problems while the audience is still forgiving.

Template from digitalmarketingmind.com/templates/digital-marketing-campaign/  ·  Created by Alston Antony  ·  Free to use in your own client work.